PROPOSAL PROJECT SUMMARY

ONE page self-contained description of the proposed activity suitable for publication; written in the third person; include a statement of objectives, methods to be employed and the potential impact of the project on advancing knowledge or education; informative to other persons working in the same or related fields and, insofar as possible, understandable to a scientifically or technically literate lay reader.

A fundamental issue in the conservation of coral reef ecosystems is an adequate knowledge of the life histories of the most important organisms; the reef building corals. Coral reproduction via annual mass spawning is a well known phenomenon, but also represents an area where there is a significant gap in our knowledge. In particular, the dispersal patterns of marine larvae, and especially those of corals, are poorly documented in coastal waters with complex hydrographic patterns. Numerical models are being used to address the need for better prediction of potential dispersal patterns, but may be of limited use if they cannot take into account the variable bathymetric features of reef areas, as well as the complicated differences among species in their larval biology. Model validation (which is essential for future predictive use of the models) by measurement of coral larvae abundance in plankton samples is made difficult by their small size, delicate nature, and our inability to tell the planulae of different coral species apart. A simple, robust and affordable system for tracking of larval dispersal patterns and model validation represents an important tool that is currently missing in the efforts to protect and restore coral reefs. The proposed project represents a new approach to the study of the dispersal patterns of coral larvae, and this new technology will be used to study the dispersal and settlement patterns of coral larvae on the upper Florida Keys reef tract. The novel, but simple system consists of a new type of particle tracer, which mimic coral larvae size and density, in conjunction with a collector array (patent pending) that can be deployed at the time of a coral mass spawning so that the trajectory of the coral larvae can be followed. The tracking will be in conjunction with a newly developed an immunoassay for the larvae of Montastraea faveolata that is highly specific for this and closely related sibling species and settlement plates to detect coral settlement rates post-spawn. What information will this give? The particle tracking system will provide a direct determination of the potential for ecological connectivity of the coral. These direct estimates of the probability that a larva spawned at location X will end up at locations (X,Y,Z…), in the appropriate time window for recruitment, represent a novel way to assess ecological connectivity on multiple spatial scales-- long-distance, large-scale tracking as well as local retention. The antibody census of coral larvae will be compared to the particle counts in order to infer changes in larval behavior over time. Since the coral larvae have been found in previous work to drift with the water as passive tracers for the first 56 hours after fertilization before they begin to swim, they should move and dilute like the particles during this time-frame. Any later observed deviation of the concentration ratio of larvae to particles will therefore give information about predation and swimming behavior. The combined data set of transfer probabilities and settlement can be compared and reconciled to yield important novel information about the relationship between transport and settlement of new coral recruits. The assessment of settlement rates of coral recruits has not been previously attempted this soon after spawning. Our overall and general working hypothesis is that the magnetically responsive design-buoyancy particles are reasonable and useful particulate models of coral larvae and when coupled with the associated magnetically attractive collectors the dispersion field of the coral larvae can be mapped synoptically at a range of temporal and spatial scales of resolution not achieved by conventional methods.

Table of Contents

|  | Page Number |
| --- | --- |
| Cover Sheet for Proposals | 1 |
| Project Summary | 2 |
| Table of Contents | 3 |
| 1.0 Project Description | 4 |
| 1.1 Situation and need | 4 |
| 1.2 Objectives | 8 |
| 1.3 Methods and approach | 9 |
| 1.4 Program management | 14 |
| 1.5 Results from prior NURP Support | 14 |
| 2.0 Literature Cited | 17 |
| 3.0 Subcontract description and budget justification | 19 |
| 4.0 Biographical sketches | 23 |
| 5.0 Current and Pending Support | 33 |
| 6.0 Special Information and Supplementary Documentation | 42 |
| 6.1 Environmental impact | 42 |
| 6.2 Cooperation from other agencies | 42 |
| 6.3 Education and outreach | 42 |
| 6.4 Letters of commitment | 42 |

1.0 PROJECT DESCRIPTION

1.1 Situation and need

1.1.a Coral recruitment -- This proposal addresses the NOAA/NURP coral research priorities of “define…keystone species…recruitment dynamics” and “understand how ecosystems function, including interrelationships between environments, populations, species, and individual organisms”. Caribbean coral reefs have suffered major losses of coral cover in the recent past due to the combined effects of coral bleaching, diseases and other environmental stressors (Gardner et al 2003). Their recovery will depend on the ability of reef corals to recruit successfully to replenish depleted adult populations. Recruitment success depends on (a) larval supply, (b) dispersal patterns during the planktonic period (which will largely determine interrelationships between environments and populations for corals), and (3) settlement and post-settlement success. The low recruitment rates observed over the past decades suggest that populations of corals on Caribbean reefs could decline to a point of ecological extinction (Hughes and Tanner 2000; Gardner et al. 2003; Pandolfi et al 2003). Given the fundamental importance of reef building corals to the entire coral reef ecosystem, it is critical to understand what factors influence their ability to achieve successful sexual recruitment. This project focuses on the need for a better understanding of the role of coral larval dispersal in coral recruitment rates in the wider Caribbean, and proposes novel approaches to the problem.

1.1.b Larval dispersal and connectivity -- Colonies of sedentary benthic organisms, such as corals, can be ecologically connected over varying spatial scales by the exchange of larvae amongst populations. Coral reproduction in the Caribbean via mass spawning is a well-known phenomenon (Szmant, 1986; 1991) that contributes to connectivity, but one where there is a significant gap in our knowledge. Despite several decades of effort (e.g. Levin, 1983; 1990; Sammarco and Andrews, 1989), the dispersal patterns of marine eggs and/or larvae, and especially those of corals, remain poorly known in coastal waters with complex hydrographic patterns (Sale et al, 2005). Numerical models are being used to address the need for better prediction of potential dispersal patterns (e.g. Pantalone et al, 2005), but will be of limited use if they cannot incorporate variable bathymetric features of reef areas, operate at a spatial scale relevant to dispersal processes, or account for variations the among species in their early life history (Largier, 2003). Oliver et al (1992) found that modeled larval dispersal patterns did not correlate well with observed larval abundance and recruitment patterns, and ascribed this to the fine-scale three-dimensional flows which occur around topographically complex structures such as coral reefs (e.g. Wolanski 1988; Wolanski and Hamner 1988;  Wolanski et al. 1989). Model verification by measurement of coral larvae abundance in plankton samples is made difficult by their small size, delicate nature, and our inability to tell the planulae of different coral species apart. Thus, there is a critical need in coral reef ecology for new tools to examine the spatial scales and extent of connectivity amongst populations in order to unravel how these populations interact with each other.

Biological oceanographers currently view scales of larval dispersal very differently than in the past. The traditional view of a homogenous “rain of larvae” has been superseded by recognition that spawning and larval behaviour as well as circulation may result in localized populations with localized larval dispersal (i.e. high reproductive connectedness or “connectivity” among populations) that have important ramifications for management, conservation, and advancing the study of population dynamics (Kinlan et al, 2005; Sale and Ludsin, 2003). Historically, quantifying marine connectivity has been constrained by the paucity of null models against which active and passive transport processes can be evaluated, by the inability to sample (observe) larvae at appropriate time and spatial scales and by the difficulties of distinguishing one species from another in a multispecies system. Another constraint in developing a realistic larval transport model is overcoming the temporal and spatial disconnect of physical oceanography models that operate on scales much greater than those relevant to larval development and settlement (Largier, 2003). Conventional drifters are useful (Arnold et al, 2005), but may be unrealistic at the scale of larvae, and without realistic drifters any null model of dispersal is highly tentative.

1.1.c Immunoassays for larvae detection – Although antibody assays to detect larval corals in a given water column have not been previously reported, the highly sensitive detection of many other organisms in water samples, particularly drinking water, has been demonstrated in a number of studies. Examples include the detection of organism specific proteins, such as a chemiluminescent antibody-based assay for oocysts of the pathogen Cryptosporidium parvum sensitive enough to detect 50 viable oocysts in 1ml of water, even turbid water (Call et al, 2001). A similar study by Lindquist et al (2001) compared four fluorescence-based immunoassays for C parvum in drinking water samples and concluded that solid phase assays, such ELISA – the method we propose using, were the most sensitive and reliable. Fluorescent antibody tests have also been used to detect the pathogenic bacteria Vibrio cholerae in freshwater plankton samples (Huq et al, 1990, Thomson et al, 1998) as well as bacteria in seawater plankton samples from the North Sea (Pernthaler, 2002), the Straits of Magellan (Caruso and Zaccone 1998) and a Mediterranean lagoon (Zaccone et al., 1996). Indeed, Caruso et al. (2002) have shown that an immunofluorescent technique is extremely sensitive in seawater and is capable of detecting 100 bacterial cells per 100 ml. Finally, Miller et al. (1991) used monoclonal antibodies to differentiate the planktonic larvae of three different species of barnacles in water samples, while Paugham et al. (2000) showed that polyclonal antisera to bivalve larvae together with enzymatic, fluorescent and magnetic secondary antibodies were capable of detecting larvae in plankton tow samples. Thus while this technique had not been previously applied specifically to coral larvae, the diverse range of organisms in these other studies indicates great promise for its application to coral larvae detection. Given the small size and fragile nature of coral larvae, using other standard plankton sampling methods (e.g. plankton tows or bottle samples with visual observation methods) to follow the dispersal of the larvae after spawning is difficult at best and virtually impossible in practice (Szmant, personal observation). Our preliminary work, funded by NOAA NURP in 2003 has shown that the immunoassay approach is not only promising, but in fact works very well for the detection of coral larvae.

1.1.d Applications, Benefits, and Importance -- NURP encourages and supports research in areas that are managed for specific uses, however the deficiencies in current larval tracking and detection methods have a direct impact on our ability to manage coral reef environments. For example, marine protected areas (MPA) are designated to provide target organisms with a refuge where they are safe from harvesting and other detrimental human activities. Among the expectations for MPAs is one that target species within the MPA will thrive, and maintain healthy adult populations that reproduce and release propagules (e.g. larvae) that can drift out of the MPA. Thus, MPAs are expected to contribute (as source) to the restoration of populations elsewhere (as sink) outside of the MPAs themselves. For the source/sink concept to be addressed with measurable success, sites must be carefully selected so that dispersal of propagules from MPAs is likely to reach areas where replenishment is needed or desirable. Therefore, a simple, robust and affordable system for the tracking of larval dispersal patterns represents an important tool that is currently missing in the efforts to protect and restore coral reefs. We hope to demonstrate here that we have such a system and propose to apply it to measurements of connectivity among the patch reefs of the upper Florida Keys. The research objectives of this proposal are focused on transport, exchange and recruitment, specifically of coral larvae, though they are equally relevant to early-stage larval fish dispersion and recruitment studies as well as tracing the fate of pollutants and chemical constituents in the ocean.  Thus, the proposed research contributes to the following specific goals outlined in the NURP FY2006 science guidelines. Bold is used to indicate specific NURP priorities and italics for interpretive commentary:

♦ Define the roll of keystone species within coral communities and determine how they sustain such roles through studies of their trophic and behavioral webs, physiological metrics in comparison to other guild members (including reproductive physiology), recruitment dynamics, and population dynamics.

Dispersal of larvae to suitable habitats for recruitment is fundamental for survival and sustainability. The study will provide data on the spatial/temporal scales of dispersal and thus measure the connectivity of potential habitats. The proposal is directly aimed at elucidating the role of larval dispersal in coral recruitment and population dynamics.

♦ Conduct research to better understand how ecosystems function, including interrelationships between environments, populations, species, and individual organisms to predict how such systems will react to change.

Data from the study will both define and quantify ecological connectivity, which is greatly influenced by larval dispersal patterns, amongst coral populations. The study proposes a new technology for quantifying physical forcings on spatial/temporal scales that are relevant to coral larval dispersal and are currently poorly understood.

♦ Conduct research to develop methods for restoration of damaged coral reefs.

Results from the study can be used to evaluate the spatial and temporal scales of connectivity of populations inside and outside of MPAs and are therefore directly relevant to determining the effectiveness of MPAs “seed” capabilities. Data from the proposed technology can be used for MPA site selection and boundary delineation.

♦ Develop models to accurately predict the effects of environmental changes (including natural events) on habitats of interest and marine managed areas

A major component of dispersal is physical forcing through oceanographic events. The proposed methodology offers a novel approach to assessing the interactions of habitat and physical forcing. The proposed new technology will provide direct observational data as well as data to validate/refine hydrodynamic models that can be used for predicting larval dispersal patterns.

♦ Develop new technologies/methods for monitoring the dynamics and status of ecosystems and communities, including chemical, physical, and biological sensors.

The proposal presents a new technology that in effect acts as a sensor for physical forcings impacting ecosystems and communities. Besides larvae, many stressors are also transported via water advection and dispersion and the proposed technology can be applied to evaluate the movement of these stressors and thus their potential for impact on critical habitats.

1.1.e Significance of Research -- The proposed research primarily addresses factors affecting recruitment and survival of a keystone marine species, reef building corals, using novel techniques: antibody tracking of potential recruits coupled with passive particle tracking.  Understanding dispersal abilities of coral larvae is important to management measures where quantitative insights are needed to determine site-selection and sizing criteria for marine protected areas.

The particle tracing system will provide a direct determination of the potential for ecological connectivity of coral populations. These direct estimates of the probability that a larva spawned at location X will end up at locations (X,Y,Z…) within the appropriate larval development and competency window for recruitment represent a novel way to assess ecological connectivity on a multiple of spatial and time scales; long-distance and large-scale far-field tracing as well as small-scale near-field local retention. The antibody assay of coral larvae will be compared to the particle collection numbers to infer changes in larval behavior and/or mortality over time. Since the coral larvae have been found in previous work to drift with the water as passive tracers for the first ~60 hours post-fertilization before they begin to swim (Szmant and Meadows, 2005), they should move and dilute in a manner similar to the novel passive particles during this time-frame. Any later observed deviation of the concentration ratio of larvae to particles will therefore provide some information about mortality, behavior and water mass associations.

The combined data set of transfer probabilities and settlement can be compared and reconciled to yield important novel information about the relationship between transport and settlement of new coral recruits. The assessment of settlement rates of coral recruits has not been previously attempted this soon after spawning.

The results of the study will be submitted to peer-reviewed journals for publication and presented at appropriate national and international conferences. It is also envisioned that the technology will be made available to both public agencies and private enterprises for use in all areas of environmental studies where advection and dispersion processes are important, such as other types of larval dispersal, sediment transport, and pollutant tracking/monitoring.

Just how far might this technology be pushed?

Let’s start with a reasonable amount (200 kg) of 450 micron particles, which translates to 5x109 particles.

Allow these to disperse to cover an area of 100 km x 100 km. (This would take 100 days with a diffusivity of 1000 m2/s). They should span the upper meter of the water column, so the particles should occupy a volume of 1010 m3, which is only one particle per 2 cubic meters.

Now, the collectors have an aperture of about 50 cm2, and in a current of 10 cm/s will sweep a volume of water of 50 cm2 x 10 cm/s x 105 s/day x 10-6 m3/cm3= 50 m3/day, a surprisingly large amount of water.  Thus, at the extreme dilution estimated above, each collector should catch about 25 particles per day, a number that allows statistical confidence in the results.

It is important to note that attempts to track conventional (i.e., rhodamine or fluorescein) dye plumes rarely succeed for timescales longer than a day or so, or space scales larger than a few km.  This is due to the difficulties in detecting tracers at large dilutions.  The exception is the man-made chemical tracer SF6, which has an exceptionally low background and detection level.  However, SF6 degasses from the water at depths less than 300 m, and must be detected using sensitive shipboard gas chromatography equipment, leading to a highly technical and expensive experiment.  Thus our particles technology greatly exceeds traditional dye techniques and approaches the level of detection of SF6 at greatly reduced costs.

1.2 Objectives

We have developed a new approach to the study of the dispersal patterns of water-born particulate materials; in this particular case, coral larvae. We are thus requesting support for the use of a new technology (Patent Pending; Apparatus, System and Method for Evaluating Fluid Systems) that relies on neutrally buoyant magnetically responsive particles (MRPs) that act as "larval mimics" and remote autonomous magnetically attractive particle collectors (MAPCs) to study the dispersal patterns of coral larvae on the patch reefs in the upper Florida Keys. The technology was conceived subsequent to a Connectivity Working Group of the World Bank funded program “Targeted Research for the Management of Coral Reefs” and exploratory work was most recently advanced with the assistance of NURC Southeastern US and Gulf of Mexico Center at UNCW and NSF–SGER funding.

The new particle tracer and collector system can be deployed at the time of a coral mass spawning so that the trajectory and a complete statistical picture of the probabilities of transport to different locations of the coral larvae can be determined. The tracking particles, which parallel larvae size and density, will be released concurrent with the spawning pulse and allowed to drift with the water and coral larvae. A pre-deployed collector array will capture the particles at potential settlement locations.

The particle tracing will also be conducted in conjunction with a new immunoassay for the larvae of Montastraea faveolata. (the assay is highly specific for this and closely related species). The reef coral, Montastraea (species complex), is a primary reef-building coral species in the Keys where it occurs on patch reefs as clusters of large boulders surrounded by smaller colonies of other hermatypic species, and on the offshore high-relief bank reefs, as enormous colonies several meters high that form major buttresses.  Many of these colonies are hundreds of years old, and have large cavities that are important shelter for reef fishes and invertebrates. Water samples will be taken along transects determined by the particle dispersal and the position of radio-drogues released concurrently into the spawn area and will be tested for the actual concentration of coral larvae using the antibody assay, as well as inspected under a microscope.

In addition, aged limestone settlement plates will be attached to substrate surrounding the collector moorings, and examined under a fluorescent microscope at the end of the two week period for the presence of newly settled coral spat.

Finally, the particle trajectory and dispersion data can be used for validation/refinement of a hydrodynamic model of the study area. Such comparisons of observational with modeled data allow not only determination of model accuracy; but can lead to improvements in model turbulence parameterizations, sub grid-scale dispersion estimates and the development of new methods for model/data analysis. As part of SACOOS and the East Florida Shelf Information System, high-resolution implementations (1-10 km horizontal resolution) of the Princeton Ocean Model are being developed to quantify the respective contributions of mesoscale features, wind-driven events, and tidal flows to advection and diffusion processes affecting larval dispersion along the Florida Keys reef tract. In an overlap with a companion proposal by J. Fiechter (RSMAS), the particle trajectory data will be used for model validation/refinement.

Our overall and general working hypothesis is that the magnetically responsive design-buoyancy particles are reasonable and useful particulate models of coral larvae and when coupled with the associated magnetically attractive collectors the dispersion field of the coral larvae can be mapped synoptically at a range of temporal and spatial scales of resolution not achieved by conventional methods.

A somewhat trivial, but entirely testable null hypothesis is that the probabilities of transport to, and from, different source and sink locations, as determined by the particles and their collection is, spatially uniform. The key here is that we can quantify not only the various trajectories in time and space, as well as their evolution, but also relative and perhaps absolute dispersion/diffusion rates and a range of scales.

The null hypothesis with regards to the immunoassay data is that the inert, passively transported particles will show the same distribution as the actual coral larvae throughout the larval competency period. The testable hypothesis here is that the coral larvae antibody assay titre in time and space is highly and linearly correlated with the coincident particle collections. Deviations in the slope of the relation from 1:1 quantify differential time/space dilution and or “survival rates” between the coral and their mimics. Non-linear and systematic deviations from the 1:1 expectation quantify differential “behavior” and or water mass mixing rates.

The null hypothesis with regards to the hydrodynamic model is that the particle dispersion field resolved by the collectors adds no additional information to the particle dispersion field determined by the numerical model. Preliminary field trials indicate that this hypothesis will be soundly rejected and that the new information made available will contribute to improved parameterization of the model, something that is also testable.

Primary Objectives

- To use the MPR and MAPC technology to track physical forcing responsible for advection and dispersion of coral propagules during and following the spawning of Montastraea faveolata.

Figure 1. Magnetically responsive particles (MRPs) in a density gradient settling column. Water density is marked on the column and illustrates that the particles have a specific gravity ranging from 1.003-1.005. Both specific gravity and size of the particles can be adjusted during manufacture.

To trace the coral spawn and particles with more conventional radio drifters and net tow samples.

- To measure coral spawn concentrations in tow samples using a new immunoassay and determine initial settlement rates.

- To provide data for validation and refinement of hydrodynamic models of the study area.

1.3 Methods and Approach

1.3.a Description of Methods -- Montastraea faveolata is hermaphroditic and broadcasts its gametes into the water column for development (Szmant 1986, 1991).  During a few, highly predictable nights a year they release gamete bundles (eggs plus sperm) that form large slicks on the ocean surface.  After fertilization, the embryos take a minimum of 3 to 5 days to develop into competent planula larvae (Szmant et al. 1997; Szmant and Miller, 2005.).  The competency period lasts up to 30 days (Szmant and Miller, 2005), but most larvae will likely attempt to settle within the first two weeks if they are in the appropriate environment.  We can predict that this species will spawn between     August 13th and 15th, 2006 when we would conduct the tracking experiment. Thus, an important pre-condition for proposing this study, that we know when we need to be in the field, can be satisfied.

Taggart and Ruddick are developing the particle and collector technology for particulate tracking in aquatic environments. In this application, the particles are released at a spawning site and due to their design size and specific gravity (Figure 1) they move with the larvae they are designed to mimic. Particle location at subsequent times across the dispersion field is determined using the simple, flow-through, moored magnetic collectors (Figure 2). Thus we avoid the need for conventional and intensive ship-based survey monitoring.  The inspiration for the technology (Taggart) arose from the attendance of the applicants at a

Figure 2. One of the 25 remote autonomous magnetically attractive particle collectors (MAPCs) moored to collect near surface particles during the 2004 Key Largo proof of concept trial.

meeting of a Global Environmental Facility Working Group on Coral Reef Connectivity, in January 2003. Development began in May 2003 funded by an NSERC Summer Undergraduate Fellowship (Jonathan Logan), Ruddick's and Taggart’s NSERC operating grant, and a UN University Contract through the Canadian Consultant's Trust Fund.  Under contract and confidential disclosure agreements, Environmental Tracing Systems Ltd (ETS) created several prototype batches of particles (Sleath, 2003) that were tested in the laboratory to ensure that their size and specific gravity were appropriate (Figure 1), and that the passive

Figure 3. The percentage of MRPs captured by the passive flow-through MAPCs as a function of flow speed of the water carrying the particles. The graph shows that particles can be captured and retained at high efficiency in flow as high as 2 m s-1 depending on the collector design and magnet arrangement (.i.e arrangement 1 & 2 vs batch-8 arrangement 1).

collectors at realistic flows could successfully capture them (Figure 3). The answer to both questions was positive (Logan, 2003).

This program will release the novel particles as a “point-source” during a local coral spawning event, trace the particles via the pre-deployed collector array and use protein antibody techniques to trace in situ variations in coral larvae concentration within the collector field. If larvae move passively with zero mortality or predation, the dilution of particles and larvae will be equal and a straight line on a correlation graph of the two will be found (Figure 4). Deviations from the straight line will tell us much about mortality and predation, and about potential active (e.g., swimming) behavior of the larvae- this is information that cannot be gleaned by current methodologies.

Immigration through mixing

Loss through mortality or settlement

[MRP]

[Larvae]

Figure 4. Schematic representation of the temporal evolution in the ratio of MRP concentration and the coral spawn antibody assay in water samples within the dispersion field. Deviations from the 1:1 line indicate either decrease in larvae through mortality or non-passive behavior (e.g. settlement) of increase of larvae via water mass mixing from other sources.

The advantages of the design-buoyancy magnetically responsive particles over dissolved dye or fluorescent particles is the remote collection capability achieved by using the remote autonomous magnetically attractive particle collectors incorporating a flow-through particle-concentrating design such that the collectors integrate the particle count over time and require no external power (Figure 2). As was demonstrated in a “proof of concept” release at Key Largo Dry Rocks in September 2004, it is not necessary to track the plume of particles using conventional tracer survey technology that typically requires intensive, 24-hour vessel work, and can require multiple coordinated vessels.  Furthermore, there are limitations on the time and distance over which it is practical to conventionally track a plume.  We believe these are significantly alleviated with our system of particles and collectors.

Figure 5

Figure 5 illustrates the results of a test of the technology in Key Largo, Florida, in September 2004 and conducted with NURP support. Three hurricanes and 2 mandatory evacuations forced a reduction in scale to a smaller array of 26 collectors and the conventional dispersion survey monitoring to <24 hours. The severe weather proved the value of the particle and collector technology in that the collectors worked flawlessly when virtually every other aspect of the program was compromised by hurricanes. The figure illustrates the particle release location at a coral spawning site (magenta star) at approximately 30.3W, 25.12N, the collectors moorings (red + ) and the associated numbers of particle collected at each (red expanding cross-hairs with areas proportional to square root of number of particles collected, successive positions of a conventional radio-tracked drifter  (yellow square) and the predicted path of the centroid of the particle patch at three depths: surface (black line), 0.5 m (magenta line) and 1 m (green line) as determined by a variant of the numerical hydrodynamic model addressed above. The particle/collector system functioned exceptionally well, showing high abundances generally where expected from the conventional, more expensive technologies (model and drifters), yet with scientifically informative differences. The particle data demonstrate that connectivity distances of several kilometers are possible in only one day, and most importantly, demonstrate that there were areas near the spawn site that were NOT reached by the released particles. Thus, the technology shows the capability of giving direct estimates of the probability of transport and dispersion estimates from a given release site.

Dixon’s lab has developed polyclonal antisera in rabbits that recognizes Montasrea faveolata and M. annularis eggs and larvae with high specificity. There is some cross reactivity with M. cavernosa, but adult material was shown to absorb out the cross reactive antibodies within the serum (~100 ml of the antiserum has been produced and it can be used at 1 in 5000 dilution, so performing the absorption with 20 ml would give us plenty of serum for future experiments). Adult M. annularis and faveolata tissue can also be used to absorb away reactivity to those two species and thus provide a serum specific for M. cavernosa. Finally, if some samples of eggs and larvae from Acropera are collected, we can hopefully raise antibodies specific to that species as well (the current antiserum does not cross-react with Acropera at all).

Once the antibodies have been developed, they can be employed in an Enzyme-Linked Immunosorbent Assay (ELISA) to detect the presence or absence of eggs and larvae in sea water samples. Previously we have shown that a 100 µm plankton tow net can collect a 10 ml sample that has been concentrated from approximately 30 m3 of seawater, in which we can detect as few as 5 larvae and with refinement we hope to be able to detect one larvae from such a sample.

During the course of the field work we will employ a plankton net to collect samples along transects through the spawning sites before, during and after the spawn. These samples will be tested for the presence or absence of eggs and larvae from the various species. The immunoassay data will be compared with the tracking particle data to elucidate changes in larval behavior and abundance as compared to the passively transported particles.

Pre-conditioned limestone settlement plates will be attached with stainless pins to the substrate surrounding a subset of the magnetic collector moorings, and retrieved at the same time the mooring samples are collected.  The plates will be examined under a fluorescent microscope to locate newly settled polyps of reef corals.  Many species of coral polyps have distinctive fluorescence that allows them to de identified to genus, as well as makes them highly visible against the complex community on the settlement plates.  One dozen plates per site will be scanned in this fashion.

1.3.b Descriptions of Major Tasks -- The prototype particles were first manufactured in the UK under contract to a consulting firm and the collectors were developed at Dalhousie University. Both aspects of the technology were tested in the Sept. 2004 Key Largo trials. Further development of particle manufacturing protocols and collectors is planned to occur starting September 2005 with funding from the World Bank. The overall methods proposed here are similar to those used in 2004 Key Largo trial with the exclusion of conventional fluorescent particles and we plan to employ a much simpler conventional tow system (primarily for larval antibody assay work) and a much larger number of collectors in a more extensive further-ranging mooring array.

The major steps will be:

- Deploy 45 moorings in an expanding circular array, each with 3 collectors (surface, subsurface and bottom) and a larval settlement plate, on an isolated patch reef in the vicinity of Key Largo Dry Rocks.

- Deploy an additional 15 moorings in three cross-shelf “fence” lines of 5 moorings each, to the north and south of the release site.

- Settlement plates will be drilled into reef substrate in the vicinity of a subset of the above mooring.

- Release ~100 kg of the drifting particles, coincident with the coral spawning.

- Release a number of conventional radio-tracked drifters to track the primary (expected) particle patch.

- Subsequent to the release use conventional ring-net and/or bongo-net tows as a generic low-resolution mapping of the particle distribution field as well as to collect plankton material for use in coral spawn protein antibody assay.

- Perform the immunoassay detection and quantification of coral larvae in the field.

- Replace the surface and subsurface collectors on a subset of the moorings to obtain a partial time series of particle arrival and relative concentration among collector moorings.

- After 7-14 days (dependent upon drift characteristics) retrieve all collector moorings, settlement plates and anchor materials.

1.3.c Study area – The particle release will be conducted in the vicinity of Key Largo Dry Rocks (25°07.59 N, 80°17.91 W). The near field collector array will be placed within 3 km of that location and the far field collector “fences” will be placed 20-50 km to the north and south.

1.3.d Proposed Dive Schedule – The collector moorings will be installed by a combination of SCUBA divers and snorkelers. Moorings will be placed in waters of less than 20 m depth. Our previous experience, in less than ideal weather conditions, has shown that each mooring can be set in less than 20 minutes. A second team of divers will set out the settlement plates. With time for vessel positioning, we should be able to install 15 to 20 moorings a day with one dive boat. A SCUBA team descends to the bottom to ensure the anchor is installed on non-living substrate. Bottom times are typically <10 minutes. Once the anchor is installed, the snorkel team adjusts the rigging so the surface collector is correctly positioned.

1.3.e Description of Facilities, Systems, and Equipment -- The project is proposed as a field operation based at the NURC facility in Key Largo. The project team and associated students will total 10 individuals that will require housing, lab and workshop space at NURC from August 5th through August 26th 2006. An additional 7 days (until September 2nd) of housing will be required for 3 of the team. The project will require 13 days of day boat (Wild Card or Research Diver) and SCUBA support with ~150 SCUBA dives of less than 20m depth during that period.

1.3.f Description of secondary support –UNCW Center for Marine Science will provide an additional 25’ day boat (Tomtate) and we will require dock space at NURC. The research team will supply the equipment required for plankton tows to collect samples for the immunoassay. A fluorometer, a microscope and a small amount of laboratory equipment (pipettes, glassware etc.) will be used in the field laboratory.

1.3.g Alternate Approach -- Alternative approaches to tracking coral larvae dispersal include using conventional technology such as dyes and chemical tracers, fixed current meters, and numerical models. However, all of the approaches have their drawbacks. Conventional tracer studies require much more vessel time/support and sophisticated sampling/analytical equipment. They are also limited in time/space scale utility by degradation and dilution. Fixed current meters can define the physical forcing in the study area, but do not actually provide observational data on dispersal patterns. Finally, numerical models need observations for development and validation. Our approach is designed to not only offer independent observational data, but to also complement and enhance numerical models that can be used to build refined predictive capability.

1.4 Program Management

1.4.a Administration -- This project will be administered jointly by Drs. Rob Whitehead and Alina Szmant at UNCW. Szmant and Ruddick will be in charge of selecting the field site and experimental time frame. Dr. Whitehead will coordinate the work schedules and data exchange.  Subcontracts will be issued to Dr. Dixon at University of Waterloo.  UNCW will disburse funds to the subcontractors according to an agreed upon payment schedule, and based on satisfactory progress.

1.4.b Roles and Assignments --This is a collaboration among five PIs from three different institutions. All five PIs have previously collaborated on coral spawn tracking projects and will work together in the field for the execution of the tracer experiment. In addition, Whitehead will contribute 1.5 and other PIs will contribute one man month to the project. Dr. Rob Whitehead, UNCW, a marine chemist with industrial polymer processing experience, will be responsible for all aspects of the particle manufacture. Dr. Alina Szmant, UNCW, a coral biologist experienced in coral reproduction and recruitment work will guide the biological aspects of the project. Whitehead and Szmant will make arrangements for ship support, permits, and other field logistics. Dr. Brian Dixon, University of Waterloo, a marine immunologist with experience in using of antibodies for ecological research, will be responsible for producing the anti-coral larvae antibodies and conducting the antibody-detection assay in the field. Drs. Barry Ruddick and Chris Taggart, Dalhousie University, the former a physical oceanographer expert in mixing and dispersion, and the latter a biological oceanographer and larval fish ecologist, both have experience with oceanographic tracer methods applied to bio logical oceanography. Ruddick and Taggart worked together in Canadian GLOBEC and are co-authors on a study of the effects of turbulence on larval feeding strategy. They will responsible for collector design and fabrication.

1.5 Results from prior NURP support

The current research group has had previous NURP support: Project # 2004-16A “Recruitment of Montastraea faveolata (species complex): Larval dispersal, settlement and post-settlement survivorship” funded through NURP Southeastern US and Gulf of Mexico Center at UNCW from 10/1/04-6/30/05 with total NURP funds of $94,015.

The previous NURP funded project had the objectives of developing and implementing a proof of concept for the technology described in the Methods section of the current proposal. However, the implementation phase for the dedicated 28 August to 10 September 2004 spawn was severely compromised by two major hurricanes (Frances and Ivan) that approached Key Largo during that period. The consequences were not trivial as there were two mandatory evacuations during the mission and the NURC facility was closed due to Hurricane Frances during the spawn period. Post-recovery from the Frances evacuation required a dive boat charter in an attempt to collect spawn on the night of 06 September, but this too was compromised by poor visibility and rough weather.  Subsequent opportunities were impossible due to the spawning period being over and the impending arrival of Hurricane Ivan. However, some spawn was collected from the few coral colonies maintained at our other field lab and these provided sufficient larvae for a reduced scope determination/validation of buoyancy/behavior and settlement. Despite the weather limitations, sufficient data were collected to demonstrate the viability of the new methods.

Antibody Assay -- One of the project’s goals was to develop an antibody-based assay that could be used to specifically detect M. faveolata eggs and larvae in seawater samples that could be used to track the larval dispersal. The polyclonal antisera to M. faveolata was developed prior to arrival in Key Largo, but had not been fully tested for potential cross reactivity with other species. Therefore, during the weather delays, tests for the cross reactivity of the antiserum using fresh coral samples were conducted. These test demonstrated that the antiserum could detect larvae, adults and eggs of M. faveolata very well with no cross reactivity with Acropora larvae, slight cross reactivity with M. cavernosa adults and larvae (20% of the level at which M. faveolata is detected) and detected larvae of M. annularis larvae about 75% as well as the M. faveolata. The cross reactivity with M. annularis may not be a problem because this species is much less common than M. faveolata and is also of interest to study. The cross reactivity with M. cavernosa is low and can be removed by either using the serum at a greater dilution (which was tested during the field trip) or pre-absorbing the antiserum with some M. cavernosa adult material. Four plankton tows, each of which sampled approximately 30 m3 of seawater, were collected on Sept 6th. No larvae were detected in those samples, but given that the volume of seawater collected could be concentrated down to 10 ml, these samples were used for spiking experiments using larvae that were produced by the lab corals. Detection of 5 and 10 larvae in those 10 ml samples was quite easy and a small reaction with samples containing 1 larva in 10 ml of seawater was also observed. This was using the antiserum at 1 in 15,000 dilution to eliminate no cross reactivity with M. cavernosa, so again this could be optimized by removing the M. cavernosa reactivity by absorption and using the antiserum at a lower dilution (1 in 5,000-10,000). This should allow detection of one larva in a plankton tow sample covering approximately 30 m3 of seawater. On the night of Sept 6th a limited number of M. faveolata eggs was collected and the antiserum detected those eggs as well as the lab samples in the lab experiments above. Further optimization will be possible in the summer of 2005 and 2006 through funding from the World Bank.

Particle tracer study -- As above, Hurricane Frances compromised the planned field trials of the novel-particle collector moorings and the vessel-mounted sampling equipment. As a result, fewer than anticipated moorings were deployed during the period 01-03 September. One “safe” mooring (as advised by NURC personnel) remained on-site during the passage of Frances and it survived completely intact and functioned well during the dispersal trial. Subsequent to the logistics of recovery from Frances, and prior to evacuation for Hurricane Ivan, a very narrow, weather-window of opportunity was exploited to deploy 26 on-site novel-particle collectors (21 near-surface and 5 near-bottom) on 07 September. This deployment represented ~50% of the planned collector deployment effort and was concentrated on the near-field aspect of the study, with virtually no far-field deployments. Point-source novel- and conventional fluorescent-particle deployment and release of the radio-tracked drifters took place early on 08 September.

Net-tow sampling system performance -- The underway vessel-mounted sampling system was designed to be comprehensive and because redundancy was built-in, it was complex.  It consisted of a 1 m2 opening side-towed neuston-net, a 12 volt pump system drawing water and particles from the net cod-end, a particle concentrator, an inline flow meter and an integrated logging system for recording time, location, flow and fluorescence signal etc.. The concentrated particle stream passed from the concentrator, though a fluorometer (for underway fluorescent particle concentration logging), a novel-particle collector (analogous to the moored in-situ collectors) and finally through a system of filters designed to retrieve all particles for later identification and enumeration. These final collections were integrated over a 2-minute period (approx. 120 m spatial resolution). However, the flow system suffered severely from the unanticipated and substantial amount of floating sea-grass that had been stirred up by Hurricane Frances. First, the fluorometer, then the inline flow meter and finally the particle concentrator had to be removed from the system due to the sea-grass clogging the system. Fortunately, the redundancy in the system design allowed us to revert to using conventional neuston net collections, though the spatial resolution was reduced to between 600 to 1000 m (5 to 10 minute integration per collection) and not in the desired continuous manner. The method allowed us to continue the survey/monitoring and radio-drifter tracking until we were forced to abandon our survey due to mandatory evacuation and field-site clean up pending Hurricane Ivan.

Sampling proceeded from around 11:00 on 08 September until dusk, and began at first light the following day, after the radio drogues and dispersion field were re-located. The sampling consisted of net-tows approximately 10 minutes in length along tracks oriented primarily in the cross-shore direction and terminated at ~11:00 on 09 September 9 due to mandatory evacuation for Hurricane Ivan.

Post-experiment assessment -- The forced hurricane evacuations had a severe impact on our ability to achieve our goals, but: Was the tracing proof of concept experiment a failure? Not for a second! Most importantly: 1) we were able to track the fluorescent and the novel-particles; 2) we were able to monitor and assay for larval antibodies using the in-situ net collections; and 3) the passive novel-particle collectors moored in-situ worked exceedingly well and beyond all expectation. We clearly demonstrated that this new and demonstrably integrated coral dispersion sampling/monitoring technique shows excellent promise.

The major conclusions are:

- The objective of validating the novel particles against fluorescent particle behavior has been achieved.  This implies that future experiments can be performed with only the novel particles and by using simpler observational techniques for larval assay (e.g. Bongo-nets).

- The collector system gave orders of magnitude more complete coverage with far less time, effort and expense than “conventional” survey systems. The collector deployment, release of novel particles, and collector recovery took about the same time as was used for one ½ day of net tow observations, but it is clear from the results that the net tows give incomplete coverage (i.e., the patch spread faster than we could survey it). The moored collectors mapped the transport of novel particles over a much larger region, giving complete coverage.

- The numbers indicate that the novel particles and collector technique should be able to observe particle motions, and hence ecological connectivity, over several 10s of km and several days, as was originally planned. We are confident, based on these results that the scale can be extended even further to 100s km and weeks.

- Both types of particles moved in conjunction with the radio-tracked drifter buoys.

- Model simulations predict particle drift in general accord with observations, and further show that the precise direction of the drift is very sensitive to particle buoyancy characteristics.  It matters a great deal whether particles are at the surface, or 0.5, or 1 m below the surface.

- The antibody titration is very sensitive, responding to as little as a single larvae per m3, and should work well in conjunction with ring-net tows to measure particle concentrations in future spawn/release experiments.

2.0 Literature cited

- Arnold, W.S.; Hitchcock, G.L.; Frischer, M.E.; Wanninkhof, R.; Sheng, Y.P. 2005. Dispersal of an introduced larval cohort in a coastal lagoon. Limnology and Oceanography 50: 587-597.

- Call JL, Arrowood M, Xie LT, Hancock K, Tsang VC. 2001. Immunoassay for viable Cryptosporidium parvum oocysts in turbid environmental water samples. J Parasitol 87:203-10

- Caruso G, Zaccone R. 1998. Distribution of Synechococcus sp. and Synechococcus bacillaris in the waters of the Straits of Magellan (April 1995-early austral autumn). New Microbiol 21:379-89

- Caruso G, Zaccone R, Crisafi E. 2000.  Use of the indirect immunofluorescence method for detection and enumeration of Escherichia coli in seawater samples.   Lett Appl Microbiol  31:274-8

Gardner, T. A.,   I. M. Côté, J. A. Gill, A. Grant, and A.R. Watkinson.  2003.  Long-term region-wide declines in Caribbean corals.  Science 301:  958-961.

Hughes, T. P. and J. E. Tanner. 2000.  Recruitment failure, life histories, and long-term decline of Caribbean corals.  Ecology 81: 2250-2263.

- Huq A, Colwell RR, Rahman R, Ali A, Chowdhury MA, Parveen S, Sack DA, Russek-Cohen E.  1990. Detection of Vibrio cholerae O1 in the aquatic environment by fluorescent-monoclonal antibody and culture methods. Appl Environ Microbiol  56:2370-3

- Kinlan, B.P., Gaines, S.D. Lester, S.E. 2005. Propagule dispersal and the scales of marine community process. Diversity and Distributions 11: 139–148

- Largier, L. 2003. Considerations in estimating larval dispersal distances from oceanographic data. Ecological Applications 13 Supplement: S71–S89

- Levin, L. A. 1983. Drift tube studies of bay-ocean water exchange and implications for larval dispersal. Estuaries 6: 364–371.

- Levin, L. A. 1990. A review of methods for labeling and tracking marine invertebrate larvae. Ophelia 32: 115–144.

- Lindquist HD, Ware M, Stetler RE, Wymer L, Schaefer FW 3rd. 2001. A comparison of four fluorescent antibody-based methods for purifying, detecting, and confirming Cryptosporidium parvum in surface waters. J Parasitol 87:1124-31.

- Logan, J. 2003. Particle Report: Determining the density of Magnetically Attractive Particles. Dalhousie University Technical Report, available from B. Ruddick, Dalhousie University.

- Miller, KM, Jones, P, Roughgarden, J. 1991. Monoclonal antibodies as species-specific probes in oceanographic research: Examples with intertidal barnacle larvae. Molecular Marine Biology and Biotechnology 1(1): 35-47

- Oliver, JK; King, BA; Willis, BL; Babcock, BC; Wolanski, E.  1992.   Dispersal of coral larvae from a lagoonal reef. 2. Comparisons between  model predictions and observed concentrations. Continental Shelf  Research 12: 873-889.

Pandolfi et al (11 co-authors). 2003.  Global Trajectories of the Long-Term Decline of Coral Reef Ecosystems.  Science 301:  955-958.

- Pantalone, P., Ruddick, B, Hatcher, B. Sheng, J. 2005. Ecological connectivity among coral reefs: Quantitative predictions of larval fish dispersal. Lagrangian Analysis and Prediction of Coastal and Ocean Dynamics Meeting abstract.

- Paugam, A,  Le Pennec, M, Genevieve, AF. 2000. Immunological recognition of marine bivalve larvae from plankton samples. Journal of Shellfish Research 19: 325-331

- Pernthaler A, Pernthaler J, Schattenhofer M, Amann R. 2002. Identification of DNA-synthesizing bacterial cells in coastal North Sea plankton. Appl Environ Microbiol  68:5728-36

- Sale, PF. and Ludsin, L.A. 2003. The extent and spatial scale of connectivity among reef fish populations: Implications for Marine Protected Areas designated for fisheries enhancement. Gulf and Caribbean Research 14: 119-128.

- Sale, P.F. et al (10 co-authors). 2005. Critical science gaps impede use of no-take fishery reserves. TRENDS in Ecology and Evolution 20: 74-80

- Sammarco, P. and J.C. Andrews. 1989.  The Helix experiment: Differential localized dispersal and recruitment patterns in Great Barrier Reef corals.  Limnol. Oceanogr. 34: 896-912.

- Sleat, R. 2003. The Production of magnetic polymer particles as tracers for monitoring the dispersion of Montasteraea: Initial industrial scale feasibility trials. Deri Technology, Cardiff, U.K. Internal Consultant's report, available from B. Ruddick, Dalhousie University.

- Szmant A.M. 1986. Reproductive ecology of Caribbean reef corals. Coral Reefs. 5: 43-54.

- Szmant, A.M. 1991. Sexual reproduction by the Caribbean reef corals Montastrea annularis and M.  cavernosa.  Mar. Ecol. Prog. Ser. 74: 13-25.

- Szmant, A.M.,  E.Weil, M.W. Miller and D.E. Colón.  1997.  Hybridization within the species complex of scleractinian coral Montastraea annularis.   Marine Biology 129: 561-572.

- Szmant, A.M. and M. G. Meadows. 2005.  Developmental changes in coral larval buoyancy and vertical swimming behavior: implications for dispersal and connectivity. , Proc 10th Int Coral Reef Symp. In Press.

Szmant, A. M. and Miller, M. W. 2005. Settlement preferences and post-settlement mortality of laboratory cultured and settled larvae of the Caribbean hermatypic corals Montastraea faveolata and Acropora palmata in the Florida Keys, USA, Proc 10th Int Coral Reef Symp. In Press

- Thomson CJ, Jesudason MV, Balaji V, Malathi B, Mukundan U, Amyes SG. 1998. The prevalence of Vibrio spp. in drinking water and environmental samples in Vellore South India. Epidemiol Infect  121:67-76

- Wolanski, E. 1988.    Island wakes shallow waters. J. Geophys. Res. 93: 1335-1336

- Wolanski, E; Hamner, WM. 1988.    Topographically controlled fronts in the ocean and their biological influence.  Science 241: 177-181

- Wolanski, E; Burrage, D; King, B.  1989.   Trapping and dispersion of coral eggs around Bowden Reef, Great Barrier  Reef, following mass coral spawning.   Cont.  Shelf  Res.  9: 479-496

- Zaccone R, Caruso G, Azzaro M. 1996. Detection of Nitrosococcus oceanus in a Mediterranean lagoon by immunofluorescence. J Appl Bacteriol 80:611